ASOJU P0 EXECUTIVE LAUNCH
& 100-CUSTOMER PILOT COMMAND CENTER

Version 1.0 | Executive Operating Document

Brand: ASOJU — Your Trusted Rep Back Home.

Purpose: provide one management-level command document for launching the P0 pilot, coordinating the first 100 customers, managing readiness, tracking KPIs, resolving risks and converting pilot learning into the next operating/product cycle.

Baseline: ASOJU P0 Technical Architecture & Data Model; API Specification & Integration Contracts; Database Schema & ERD; Security, Privacy & Trust Architecture; QA/UAT/Pilot Acceptance Test Plan; Production Operations & Support Runbook; and the established ASOJU P0 GTM/Customer Experience workstream.

# 1. Executive Mandate

The P0 pilot is a controlled proof that ASOJU can reliably deliver its core promise: trusted representation back home for customers who need someone credible to act, verify, coordinate and report on their behalf.

The objective is not maximum volume. The objective is repeatable trust, operational reliability and evidence-backed outcomes.

# 2. P0 Pilot Objectives

| Objective | Definition of Success |
| --- | --- |
| Customer value | Customers understand what ASOJU will do, receive a credible outcome and can see evidence of execution. |
| Operational reliability | Cases move through the defined lifecycle with accountable ownership and clear next actions. |
| Trust | Scope, payment, representative, evidence, QC and delivery remain traceable. |
| Commercial proof | The pilot validates willingness to pay and identifies repeatable service economics. |
| Quality | QC/rework mechanisms catch execution issues before customer delivery. |
| Learning | The first 100 customers generate prioritized evidence for product/GTM/operations decisions. |
| Scale readiness | The team knows which constraints must be fixed before materially increasing volume. |

# 3. Command Center Principles

One source of truth for pilot status.

Every red metric has an owner.

Every active case has a next action.

Every material risk has a decision date.

Every launch gate has explicit evidence.

Customer trust outranks vanity volume.

Manual fallback is acceptable during P0 when it protects service quality.

Automate only after the workflow is understood and repeatable.

# 4. Executive Dashboard

| Dimension | Core KPI | Cadence | Owner |
| --- | --- | --- | --- |
| Demand | Qualified leads | Daily/Weekly | GTM/Concierge |
| Conversion | Lead → case conversion | Weekly | GTM/Product |
| Activation | Case → paid/active | Weekly | GTM/Finance |
| Operations | Active cases by state | Daily | Operations |
| Reliability | SLA adherence | Daily/Weekly | Operations |
| Field | On-time execution | Weekly | Field Ops |
| Quality | QC first-pass rate | Weekly | QC |
| Rework | Rework rate | Weekly | QC/Ops |
| Customer | Satisfaction/trust signal | Weekly | CX |
| Commercial | Payment success/reconciliation | Daily/Weekly | Finance |
| Growth | Referral/repeat intent | Weekly | GTM/CX |
| Risk | P0/P1 incidents | Immediate/Weekly | Technology/Risk |

# 5. 100-Customer Pilot Funnel

The funnel should be managed as a sequence, not a single acquisition number.

| Stage | Command Metric | Management Question |
| --- | --- | --- |
| Reach | Qualified target accounts/people | Are we reaching the right ICP? |
| Engaged | Meaningful conversations | Is the problem resonating? |
| Qualified | Validated use cases | Are we selecting cases ASOJU can deliver well? |
| Scoped | Approved scope opportunities | Can we define the work clearly? |
| Quoted | Quotes issued | Is the value proposition commercially clear? |
| Paid/Active | Paid or otherwise activated cases | Will customers commit? |
| Executed | Field work completed | Can the operating system deliver? |
| QC Passed | Quality-approved cases | Is the output trustworthy? |
| Delivered | Customer outcome delivered | Did ASOJU complete the promise? |
| Satisfied | Positive outcome/feedback | Would they use or recommend ASOJU? |

# 6. 100-Customer Pilot Targeting

The 100-customer target should be treated as a controlled cohort, not a blind volume target.

Prioritize the agreed Ideal Customer Profile.

Prioritize use cases that are operationally repeatable.

Prefer cases where evidence-backed representation creates obvious value.

Avoid overloading the pilot with unusually complex or high-risk cases before the core workflow is proven.

Track source/channel for every qualified lead.

Track service mix so the pilot does not accidentally validate only one narrow use case.

# 7. Customer Cohort Design

| Cohort | Purpose |
| --- | --- |
| Early Trust Cohort | Validate the core proposition with highly engaged customers. |
| Referral/Network Cohort | Test trust transfer and warm acquisition. |
| Diaspora Community Cohort | Test repeatable community-led acquisition. |
| Professional/Partner Cohort | Test trusted intermediary channels. |
| Broader Pilot Cohort | Test the operating model under more normal demand. |

Exact cohort sizes should be set by the GTM owner based on the approved 100-customer acquisition plan.

# 8. Launch Readiness Framework

| Gate | Evidence Required | Decision Owner |
| --- | --- | --- |
| Product | Golden-path workflow passes UAT. | Product |
| Technology | Critical APIs, database, monitoring and recovery ready. | Technology |
| Security/Trust | Security launch gates pass. | Technology/Risk |
| Operations | Runbook, owners, queues and fallback ready. | Operations |
| Field | Eligible representatives and execution process ready. | Field Ops |
| QC | QC/rework/report gating proven. | QC |
| Finance | Payment/reconciliation/refund process ready. | Finance |
| CX | Customer communication/support process ready. | CX/Operations |
| GTM | Acquisition funnel and lead handling ready. | GTM |
| Management | Risks accepted; command structure active. | Executive Sponsor |

# 9. Go / Conditional Go / No-Go

| Decision | Criteria |
| --- | --- |
| GO | All mandatory gates pass; no P0 blockers; acceptable P1 exposure; accountable owners confirmed. |
| GO WITH CONDITIONS | Only bounded, documented risks with workaround, owner and deadline. |
| NO-GO | Core golden path broken; material security/payment/evidence failure; no safe fallback; or operational ownership absent. |

# 10. Executive Launch Checklist

Pilot ICP and customer target approved.

Primary service/use cases approved.

100-customer acquisition plan approved.

Product build meets P0 acceptance criteria.

Security/privacy launch gates pass.

Payment and reconciliation process tested.

Representative network ready.

QC capacity ready.

Customer support path active.

Operations dashboard active.

Incident command structure active.

Manual fallback tested.

Weekly executive review scheduled.

Pilot decision log created.

# 11. First 10 Customers — White-Glove Mode

The first ten customers should be treated as controlled learning cases.

Review the request before acceptance.

Confirm scope and customer expectation explicitly.

Assign a named owner.

Monitor the case through each state.

Review evidence closely.

Capture customer feedback immediately after delivery.

Document any friction.

Do not hide manual work; identify it as a learning signal.

Fix obvious systemic defects before increasing volume.

# 12. Customers 11–25 — Repeatability Test

Reduce unnecessary manual intervention.

Confirm the workflow remains understandable to the team.

Track recurring customer questions.

Track recurring field exceptions.

Measure QC/rework patterns.

Validate that the same service can be delivered consistently.

Begin formal cohort/channel comparison.

# 13. Customers 26–50 — Operating System Test

Increase controlled throughput.

Stress assignment and scheduling.

Stress evidence/QC capacity.

Review payment/reconciliation volume.

Validate support response.

Measure SLA performance.

Identify bottlenecks that will prevent 100+ customer operation.

# 14. Customers 51–100 — Controlled Scale Test

Operate with standard runbooks rather than founder-dependent intervention.

Monitor queue health daily.

Test cross-functional handoffs.

Track customer trust and satisfaction.

Identify service types that should be expanded, restricted or redesigned.

Measure economics and operational capacity.

Prepare scale/no-scale recommendation.

# 15. Weekly Executive Review Agenda

Pilot scorecard.

Customer funnel.

Active cases and operational health.

Quality/QC.

Customer trust and complaints.

Commercial/payment health.

Technology/security incidents.

Field performance.

Top five risks.

Decisions required.

Learning converted into actions.

Next-week priorities.

# 16. Weekly Executive Scorecard

| Metric | Target/Threshold | Actual | Status | Owner | Action |
| --- | --- | --- | --- | --- | --- |
| Qualified leads | Set by GTM plan |  |  |  |  |
| Cases created | Set by pilot cohort plan |  |  |  |  |
| Paid/active cases | Set by commercial plan |  |  |  |  |
| Completed cases | Set by operating capacity |  |  |  |  |
| QC first-pass | Set quality threshold |  |  |  |  |
| Rework rate | Set quality threshold |  |  |  |  |
| SLA adherence | Set operating threshold |  |  |  |  |
| Customer satisfaction | Set CX threshold |  |  |  |  |
| Payment reconciliation | Target near-complete |  |  |  |  |
| P0/P1 incidents | Zero/controlled |  |  |  |  |
| Referral/repeat intent | Track trend |  |  |  |  |

# 17. Risk Register

| Risk | Likelihood | Impact | Mitigation | Owner | Trigger |
| --- | --- | --- | --- | --- | --- |
| Demand exceeds operations | Medium | High | Cap intake and increase capacity deliberately. | Operations | Queue/SLA threshold. |
| Insufficient qualified representatives | Medium | High | Maintain eligibility bench and partner pipeline. | Field Ops | Assignment delay. |
| Evidence quality inconsistent | Medium | High | Strengthen requirements/training/QC. | QC | Rework trend. |
| Payment/reconciliation issue | Low/Medium | High | Provider testing + Finance reconciliation. | Finance | Payment exception. |
| Customer expectation mismatch | Medium | High | Stronger scoping and communication. | CX/Ops | Complaint/rework. |
| Security/privacy incident | Low | Critical | Access controls, monitoring, incident runbook. | Technology/Risk | Security alert. |
| AI output error | Medium | Medium/High | Human review and tool boundaries. | Product/Technology | AI evaluation failure. |
| Founder/key-person dependency | Medium | High | Runbook and delegated ownership. | Management | Repeated manual intervention. |
| Low repeatability across services | Medium | High | Narrow service mix and standardize. | Product/Ops | High variance. |
| Pilot learning not converted | Medium | Medium | Weekly decision log and backlog review. | Product | Repeated issue. |

# 18. Decision Log

| Decision ID | Date | Decision | Evidence | Owner | Follow-up Date | Status |
| --- | --- | --- | --- | --- | --- | --- |
| DEC-001 |  |  |  |  |  |  |
| DEC-002 |  |  |  |  |  |  |
| DEC-003 |  |  |  |  |  |  |
| DEC-004 |  |  |  |  |  |  |
| DEC-005 |  |  |  |  |  |  |

# 19. P0/P1 Escalation Rules

P0 security, payment, authorization, evidence exposure or major customer-harm issue: immediate incident command.

P1 core workflow failure: accountable owner within the operating day and executive visibility.

Repeated P2 issue across multiple customers: promote to P1/product decision review.

Any issue affecting trust in a repeatable way should be reviewed even if technically low severity.

# 20. Customer Trust Command Metrics

| Signal | Why It Matters |
| --- | --- |
| Customer understood scope | Prevents expectation mismatch. |
| Customer knew next step | Measures operational transparency. |
| Customer received evidence | Core proof of representation. |
| Customer accepted outcome | Value realization. |
| Complaint rate | Trust failure signal. |
| Repeat intent | Retention signal. |
| Referral intent | Trust transfer signal. |
| Time to resolution | Operational confidence. |

# 21. Operational Capacity Dashboard

| Capacity | Monitor |
| --- | --- |
| Concierge | Qualified leads per owner; response time. |
| Operations | Active cases per owner; overdue next actions. |
| Field | Available eligible agents; assignments per agent. |
| QC | Pending reviews; review age. |
| Finance | Pending reconciliation/payment exceptions. |
| Support | Open cases by priority. |
| Technology | Incidents, latency, integration health. |

# 22. GTM-to-Operations Handoff

GTM creates/records lead source.

Concierge validates customer need.

Qualified lead becomes case.

Operations confirms scope readiness.

Commercial path is approved.

Payment state is confirmed.

Operations takes execution ownership.

Customer receives clear next step.

Case is tracked through completion.

Feedback and referral intent return to GTM/CX.

# 23. Product-to-Operations Handoff

Every new workflow change has an owner.

State-machine changes are documented.

API/database changes have QA coverage.

Runbook changes accompany material operational changes.

Customer-facing wording is aligned.

Monitoring is updated where new failure modes exist.

Rollback/fallback is defined before release.

# 24. Pilot Learning Loop

LEARN → DECIDE → BUILD/CHANGE → TEST → DEPLOY → MEASURE → LEARN

Capture observed problem.

Separate symptom from root cause.

Estimate customer/operational impact.

Decide whether to fix, standardize, defer or stop.

Assign owner.

Add to backlog/operating plan.

Implement controlled change.

Test.

Measure after release.

Close the loop.

# 25. What the Pilot Must Prove

| Hypothesis | Evidence |
| --- | --- |
| Customers value trusted representation. | Conversion, payment and feedback. |
| ASOJU can define work clearly. | Scope approval and low expectation-related rework. |
| Customers will pay for defined outcomes. | Payment/quote data. |
| ASOJU can coordinate trusted representatives. | Assignment acceptance and execution. |
| Evidence increases confidence. | QC pass and customer feedback. |
| The operating model can scale beyond founder intervention. | Owner/queue/runbook performance. |
| Customers will return/refer. | Repeat/referral intent. |
| The chosen service mix is operationally repeatable. | Cycle time, QC, rework and margin patterns. |

# 26. What the Pilot Must Not Optimize For

Vanity lead volume.

Maximum number of service categories.

Automation for its own sake.

Artificially low pricing that cannot support future economics.

Founder-only heroics.

Fast delivery achieved by bypassing scope/QC/security.

Growth that creates an unmanageable support burden.

# 27. Scale Decision at Customer 100

| Outcome | Meaning |
| --- | --- |
| Scale | Core workflow is repeatable, trust is strong, unit economics and capacity are credible. |
| Refine then scale | Value is proven but specific operational/product bottlenecks remain. |
| Narrow | Some services/channels work; others should be restricted. |
| Pivot | Core hypothesis is not sufficiently validated. |
| Pause | Operational/security/economic risk prevents responsible expansion. |

# 28. Executive Readiness Scorecard

| Dimension | Green | Amber | Red |
| --- | --- | --- | --- |
| Customer value | Strong evidence of value. | Mixed feedback. | Customers do not perceive meaningful value. |
| GTM | Predictable qualified pipeline. | Pipeline uneven. | No repeatable acquisition signal. |
| Operations | Cases run reliably. | Manual bottlenecks. | Frequent failures. |
| Quality | High first-pass QC. | Manageable rework. | Quality unreliable. |
| Trust | Low material complaints; strong confidence. | Some concerns. | Material trust failures. |
| Commercial | Payments/economics credible. | Needs optimization. | Economics not viable. |
| Technology | Stable and observable. | Minor instability. | Core workflow unreliable. |
| Security | Launch gates remain green. | Controlled gaps. | Any material security failure. |
| Team | Ownership distributed. | Some key-person dependency. | Founder-dependent operation. |

# 29. Executive Command Roles

| Role | Accountability |
| --- | --- |
| Executive Sponsor | Go/no-go, major risk and resource decisions. |
| Product Lead | Product priorities, learning loop and customer value. |
| Technology Lead | Platform reliability, security and releases. |
| Operations Lead | Case flow, SLA, assignment and escalation. |
| GTM Lead | Acquisition, funnel and channel performance. |
| CX/Concierge Lead | Customer intake, communication and trust. |
| Field Lead | Representative capacity and performance. |
| QC Lead | Evidence quality and report readiness. |
| Finance Lead | Payment/reconciliation/refunds/economics. |

# 30. 30/60/90-Day Pilot Management View

| Period | Primary Focus |
| --- | --- |
| Days 0–30 | Launch safely, validate golden path, learn from first customers. |
| Days 31–60 | Increase controlled volume, remove repeat bottlenecks, validate service/channel patterns. |
| Days 61–90 | Prove repeatability, refine economics/capacity, make scale decision. |

# 31. Launch-Day Command Checklist

Confirm all launch gates are green.

Confirm team owners are available.

Confirm dashboards and alerts.

Confirm payment test/monitoring.

Confirm support/escalation contacts.

Confirm representative availability.

Confirm customer communication templates.

Confirm incident channel/process.

Confirm manual fallback.

Confirm executive decision owner.

# 32. First Live Case Command Checklist

Verify customer/case.

Verify approved scope.

Verify commercial/payment status.

Verify assigned representative.

Verify customer knows next step.

Monitor execution.

Verify evidence.

Verify QC.

Verify report/delivery.

Capture feedback.

Review case as a learning artifact.

# 33. Executive Review Template

| Item | Status | Evidence | Decision/Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| Pilot funnel |  |  |  |  |  |
| Operations |  |  |  |  |  |
| Quality |  |  |  |  |  |
| Customer trust |  |  |  |  |  |
| Commercial |  |  |  |  |  |
| Technology/security |  |  |  |  |  |
| Field network |  |  |  |  |  |
| Top risks |  |  |  |  |  |
| Key learning |  |  |  |  |  |

# 34. P0 Command Center No-Go Conditions

Executive team cannot identify the accountable owner for active cases.

Golden path cannot complete safely.

Security/evidence/payment controls are not proven.

Operations has no manual fallback.

Customer complaints cannot be owned/resolved.

QC can be bypassed.

Pilot volume exceeds operational capacity without an explicit intake-control mechanism.

Key metrics are unavailable or misleading.

Critical risks have no owner or decision date.

The pilot is optimizing acquisition faster than the organization can deliver trusted outcomes.

# 35. Final Executive Principle

The first 100 customers are not simply customers. They are the evidence base for whether ASOJU has built a trustworthy, repeatable operating system.

The command center exists to make that evidence visible: what is working, what is failing, what customers are telling us, what the operation can sustain, and what must change before the next level of scale.

# 36. Governance

Document owner: ASOJU Executive Sponsor / Product / Operations.

Version: 1.0 | P0 Pilot.

Use this document as the executive layer above the detailed P0 technical, operational, security, QA and GTM documents.