ASOJU P0 PRODUCT BACKLOG
& ENGINEERING SPRINT PLAN

Version 1.0 | 90-Day P0 Build

Brand: ASOJU — Your Trusted Rep Back Home.

Purpose: translate the locked P0 platform requirements and screen-by-screen UX specification into an executable engineering backlog, prioritized build sequence, acceptance criteria, dependencies and 90-day delivery plan.

# 1. Source Baseline

This backlog is derived from the ASOJU P0 Technology & Platform Requirements Specification and P0 Screen-by-Screen UX Specification. It preserves the Concierge-first operating model, case-centric workflow, evidence/QC controls and human accountability for high-risk decisions.

Build principle:

BUILD THE OPERATION BEFORE AUTOMATING IT.

# 2. P0 Outcome

At the end of the initial build, ASOJU should be able to execute the golden path end-to-end:

REQUEST → CASE → SCOPE → QUOTE → PAYMENT → ASSIGNMENT → EXECUTION → EVIDENCE → QC → REPORT → CLOSE → REPEAT / MONITOR / REFER

The P0 objective is a reliable operational product, not a feature-complete marketplace.

# 3. Prioritization Framework

| Priority | Meaning |
| --- | --- |
| P0 / Must | Required for golden-path pilot execution or trust/safety/control. |
| P0-lite | Required in simplified form for pilot; deeper automation can follow. |
| P1 / Later | Valuable but not required to prove the P0 model. |
| Deferred | Explicitly outside initial build scope. |

# 4. Engineering Epics

| Epic | Outcome | Priority |
| --- | --- | --- |
| E01 Foundation & Security | Stable application foundation, authentication, authorization, environments and audit. | P0 |
| E02 Customer Intake & Concierge | Customer can state intent and create a structured request. | P0 |
| E03 Case Management | Case becomes the single operational source of truth. | P0 |
| E04 Scope & Quote | Operations can define scope and issue controlled quotes. | P0 |
| E05 Payment | Approved customer payment activates the case. | P0 |
| E06 Assignment & Scheduling | Eligible field representatives can be assigned and scheduled. | P0 |
| E07 Field Mobile | Representative can execute scope and submit evidence. | P0 |
| E08 Evidence & QC | Evidence is linked, reviewed and controlled. | P0 |
| E09 Reporting & Delivery | Customer receives the approved outcome/report. | P0 |
| E10 Notifications & SLA | Critical status and action events are communicated. | P0 |
| E11 Escalations & Incidents | Risk, complaint, scope and specialist issues are controlled. | P0 |
| E12 Customer Experience | Customer can track, act, review reports and continue service. | P0 |
| E13 Provider Network | Representative profiles, certification, status and performance. | P0-lite |
| E14 Commercial & Economics | Quote/payment/cost/contribution records support unit economics. | P0 |
| E15 Management Dashboard | Growth, customer, operations, quality and financial control. | P0-lite |
| E16 AI Assistance | Controlled AI intake, summarization, routing and drafting. | P0-lite |
| E17 Analytics & Instrumentation | Product and operating events support learning. | P0-lite |
| E18 Reliability & Launch | Testing, monitoring, backup, support and deployment readiness. | P0 |

# 5. Backlog Structure

Each backlog item should contain:

User story / job to be done.

Acceptance criteria.

Dependencies.

Priority.

Owner.

Estimate.

Status.

Release/sprint.

Validation evidence.

# 6. E01 — Foundation & Security

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E01-01 | As a user, I can securely authenticate. | Authentication works; sessions expire securely; unauthorized access is blocked. | P0 |
| E01-02 | As an administrator, I can assign roles. | Customer, Concierge, Operations, Field, QC, Finance and Admin roles enforce permissions. | P0 |
| E01-03 | As the system, I enforce case-level authorization. | Users cannot access cases outside their authorized scope. | P0 |
| E01-04 | As Operations, I can see material audit events. | Status, approval, assignment and evidence actions are traceable. | P0 |
| E01-05 | As staff/admin, I can use MFA. | MFA enabled for privileged roles. | P0 |
| E01-06 | As the system, secrets are protected. | No production secrets embedded in code; managed secret storage used. | P0 |
| E01-07 | As the platform, backups exist. | Backup and restore procedure tested before pilot. | P0 |
| E01-08 | As the team, environments are separated. | Development/test/production boundaries are defined. | P0 |

# 7. E02 — Customer Intake & Concierge

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E02-01 | As a customer, I can start by telling ASOJU what I need. | One primary CTA opens Concierge intake. | P0 |
| E02-02 | As a customer, I can describe my request naturally. | Free-text input is supported. | P0 |
| E02-03 | As Concierge, I can structure intent. | Objective, location, timing, concern and expected outcome can be captured. | P0 |
| E02-04 | As a customer, I can confirm the request summary. | Customer can approve or correct structured summary. | P0 |
| E02-05 | As Concierge, I can see new leads in an inbox. | New requests are queued with age, owner and next action. | P0 |
| E02-06 | As Concierge, I can hand off without losing context. | Conversation and structured fields remain attached to lead/case. | P0 |
| E02-07 | As a customer, I can request human help. | Human handoff is explicit and preserves context. | P0 |
| E02-08 | As Concierge, I can mark a lead qualified. | Minimum qualification fields are complete before qualification status. | P0 |

# 8. E03 — Case Management

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E03-01 | As the system, I create a unique Case ID. | Immutable ID is generated and displayed. | P0 |
| E03-02 | As Operations, I can see the case pipeline. | Locked statuses are visible and filterable. | P0 |
| E03-03 | As Operations, I can open a case detail view. | Customer, intent, scope, commercial, delivery, evidence, QC, report, risk and audit panels are accessible. | P0 |
| E03-04 | As the system, I enforce valid state transitions. | Invalid transitions are blocked. | P0 |
| E03-05 | As an owner, I can assign a next action. | Every active case has an accountable owner and next action. | P0 |
| E03-06 | As the system, I preserve status history. | Material changes record actor and timestamp. | P0 |
| E03-07 | As Operations, I can place a case on hold. | Reason and owner are required. | P0 |
| E03-08 | As Operations, I can escalate a case. | Escalation creates linked risk/issue record. | P0 |

# 9. E04 — Scope & Quote

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E04-01 | As Operations, I can select an approved service. | Service definitions are configurable. | P0 |
| E04-02 | As Operations, I can define included scope. | Scope is explicit and versioned. | P0 |
| E04-03 | As Operations, I can define exclusions. | Exclusions are visible in quote. | P0 |
| E04-04 | As Operations, I can define evidence and deliverable. | Required evidence and report are captured. | P0 |
| E04-05 | As Operations, I can calculate quote components. | Base, travel, complexity, evidence/reporting, third-party and urgency components can be recorded. | P0 |
| E04-06 | As a customer, I can review a quote. | Scope, exclusions, timing, fee, deliverable and terms are visible. | P0 |
| E04-07 | As a customer, I can approve a quote. | Approval is explicit and auditable. | P0 |
| E04-08 | As Operations, I can revise scope after approval. | New scope version requires controlled re-approval where material. | P0 |

# 10. E05 — Payment

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E05-01 | As a customer, I can pay an approved quote. | Approved payment provider is integrated. | P0 |
| E05-02 | As the system, I link payment to Case ID. | Payment intent/status is case-linked. | P0 |
| E05-03 | As Operations, I can see payment status. | Pending, received, failed and refund states are supported. | P0 |
| E05-04 | As Finance, I can reconcile payments. | Case-to-payment record is traceable. | P0 |
| E05-05 | As the system, I prevent premature activation. | Configured payment control is satisfied before assignment readiness. | P0 |

# 11. E06 — Assignment & Scheduling

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E06-01 | As Operations, I can view eligible representatives. | Coverage, capability, status and capacity are visible. | P0 |
| E06-02 | As Operations, I can assign a representative. | Assignment is linked to case and scope. | P0 |
| E06-03 | As representative, I can accept/decline. | Acceptance is explicit and timestamped. | P0 |
| E06-04 | As the system, I check conflicts. | Potential conflict blocks/flags assignment as configured. | P0 |
| E06-05 | As Operations, I can schedule work. | Date/time/location are recorded. | P0 |
| E06-06 | As customer, I can see relevant schedule status. | Customer receives appropriate scheduling update. | P0 |

# 12. E07 — Field Mobile

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E07-01 | As a representative, I can see today's assignments. | Only authorized active assignments appear. | P0 |
| E07-02 | As representative, I can open assignment instructions. | Objective, scope, exclusions, checklist, evidence and safety are visible. | P0 |
| E07-03 | As representative, I can complete a checklist. | Structured observations and completion state are captured. | P0 |
| E07-04 | As representative, I can capture evidence. | Required evidence types can be captured and linked. | P0 |
| E07-05 | As representative, I can flag an exception. | Safety, scope, access, evidence or specialist issues can be escalated. | P0 |
| E07-06 | As representative, I can review before submission. | Missing required evidence/fields are surfaced. | P0 |
| E07-07 | As representative, I can submit. | Case moves to EVIDENCE SUBMITTED and audit event is created. | P0 |
| E07-08 | As representative, I can work with unreliable connectivity where practical. | Safe local capture/sync strategy is implemented or explicitly tested as a constraint. | P0 |

# 13. E08 — Evidence & QC

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E08-01 | As the system, every evidence item has an ID. | Unique evidence ID linked to Case ID. | P0 |
| E08-02 | As QC, I can review evidence in one queue. | Evidence, scope and field notes are visible together. | P0 |
| E08-03 | As QC, I can approve. | QC outcome and reviewer are recorded. | P0 |
| E08-04 | As QC, I can request rework. | Reason and required correction are recorded. | P0 |
| E08-05 | As QC, I can escalate. | Material issues create escalation path. | P0 |
| E08-06 | As the system, evidence access is controlled. | Unauthorized users cannot access evidence. | P0 |
| E08-07 | As Operations, I can see rework rate. | Rework events are measurable. | P0 |

# 14. E09 — Reporting & Delivery

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E09-01 | As Operations, I can create a customer report. | Report links to approved scope and evidence. | P0 |
| E09-02 | As QC, I can approve report readiness. | Only approved report can become REPORT READY. | P0 |
| E09-03 | As customer, I can view report. | Report accessible from case. | P0 |
| E09-04 | As customer, I can access relevant evidence. | Access follows policy and case authorization. | P0 |
| E09-05 | As the system, I record delivery. | Delivery timestamp/channel is recorded. | P0 |

# 15. E10 — Notifications & SLA

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E10-01 | As customer, I receive critical case updates. | Quote, payment, assignment, schedule, delay, report and closure events notify appropriately. | P0 |
| E10-02 | As Operations, I receive action alerts. | Overdue, QC, escalation and payment exceptions surface. | P0 |
| E10-03 | As representative, I receive assignment alerts. | New/changed assignment is communicated. | P0 |
| E10-04 | As system, SLA clocks are configurable. | SLA values can change without code deployment. | P0 |
| E10-05 | As Operations, I can see at-risk cases. | Age and SLA risk are visible. | P0 |

# 16. E11 — Escalations & Incidents

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E11-01 | As any authorized operator, I can create an escalation. | Reason, severity, owner and next decision are required. | P0 |
| E11-02 | As Operations, I can manage open escalations. | Queue supports aging and ownership. | P0 |
| E11-03 | As representative, I can flag safety or scope issues. | Normal execution can be paused pending decision. | P0 |
| E11-04 | As Operations, I can record complaint outcomes. | Complaint is linked to customer/case. | P0 |
| E11-05 | As management, I can see incident history. | Material incidents remain auditable. | P0 |

# 17. E12 — Customer Experience

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E12-01 | As customer, I can view active cases. | Case list and status available. | P0 |
| E12-02 | As customer, I can see next action. | Each active case shows one clear next step. | P0 |
| E12-03 | As customer, I can respond to action requests. | Approval/clarification actions work from case. | P0 |
| E12-04 | As customer, I can view reports. | Delivered reports are accessible. | P0 |
| E12-05 | As customer, I can provide feedback. | Feedback is stored against case/customer. | P0 |
| E12-06 | As customer, I can request monitoring/repeat. | Post-case continuation flow exists. | P0 |
| E12-07 | As customer, I can refer someone. | Referral capture is supported in simplified form. | P0-lite |

# 18. E13 — Provider Network

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E13-01 | As Operations, I can create provider/agent profile. | Identity, coverage, capability and status captured. | P0-lite |
| E13-02 | As Operations, I can record certification. | Training/assessment state is visible. | P0-lite |
| E13-03 | As Operations, I can restrict/suspend a representative. | Restricted status prevents inappropriate assignment. | P0 |
| E13-04 | As Operations, I can see performance. | On-time, QC, rework and feedback metrics visible. | P0-lite |
| E13-05 | As Operations, I can track capacity. | Availability supports assignment decisions. | P0-lite |

# 19. E14 — Commercial & Economics

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E14-01 | As Finance, I can record direct case costs. | Representative, travel, third-party and other direct costs supported. | P0 |
| E14-02 | As Finance, I can calculate contribution. | Revenue minus direct case costs. | P0 |
| E14-03 | As management, I can see contribution margin. | Case/service margin is visible. | P0 |
| E14-04 | As Commercial, I can track discounts. | Discount amount and reason are recorded. | P0 |
| E14-05 | As Finance, I can track refunds/credits. | Refund/credit linked to case. | P0 |
| E14-06 | As Commercial, I can attribute lead source. | Source stored for CAC analysis. | P0-lite |

# 20. E15 — Management Dashboard

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E15-01 | As management, I can see growth. | Leads, conversion, AOV and channel metrics. | P0-lite |
| E15-02 | As management, I can see customer health. | Satisfaction, complaints, repeat, recurring, referral. | P0-lite |
| E15-03 | As Operations, I can see bottlenecks. | Case aging, overdue, QC and escalations. | P0 |
| E15-04 | As management, I can see quality. | QC first-pass, rework and evidence metrics. | P0-lite |
| E15-05 | As Finance, I can see economics. | Revenue, direct costs, contribution, CAC where available. | P0-lite |
| E15-06 | As management, I can see scale readiness. | Demand, delivery, quality, customer, field network, economics, cash and process indicators. | P0-lite |

# 21. E16 — AI Assistance

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E16-01 | As customer, I can use AI Concierge. | AI asks relevant questions and captures structured intent. | P0-lite |
| E16-02 | As AI, I can summarize request. | Summary grounded in conversation. | P0-lite |
| E16-03 | As AI, I can suggest service route. | Recommendation is reviewable by human. | P0-lite |
| E16-04 | As Concierge, I can use AI to draft responses. | Draft grounded in case state and approved templates. | P0-lite |
| E16-05 | As Operations, I can use AI to summarize case. | Summary includes source/context and does not invent facts. | P0-lite |
| E16-06 | As system, high-risk actions require human approval. | AI cannot bypass deterministic authorization. | P0 |
| E16-07 | As product team, I can evaluate AI quality. | Prompts/model versions and evaluation examples can be tracked. | P0-lite |

# 22. E17 — Analytics & Instrumentation

| ID | Event | Purpose |
| --- | --- | --- |
| E17-01 | request_started | Top-of-funnel intent. |
| E17-02 | request_submitted | Lead conversion. |
| E17-03 | summary_confirmed | Intent clarity. |
| E17-04 | case_created | Operational conversion. |
| E17-05 | quote_viewed | Commercial engagement. |
| E17-06 | quote_approved | Quote conversion. |
| E17-07 | payment_completed | Paid-case conversion. |
| E17-08 | assignment_accepted | Delivery readiness. |
| E17-09 | evidence_submitted | Field completion. |
| E17-10 | qc_rework | Quality friction. |
| E17-11 | report_opened | Delivery engagement. |
| E17-12 | feedback_submitted | Customer experience. |
| E17-13 | monitoring_selected | Recurring intent. |
| E17-14 | referral_started | Organic growth. |

# 23. E18 — Reliability & Launch

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| E18-01 | As product, I have automated tests for critical state transitions. | Golden-path and invalid-transition tests pass. | P0 |
| E18-02 | As product, I can monitor production errors. | Error logging/alerting is active. | P0 |
| E18-03 | As operations, I have a support runbook. | Common incidents have response procedures. | P0 |
| E18-04 | As the team, I can deploy safely. | Rollback strategy tested. | P0 |
| E18-05 | As the team, I can recover data. | Restore procedure tested. | P0 |
| E18-06 | As security, I can validate access controls. | Role/case authorization test suite passes. | P0 |
| E18-07 | As product, I can conduct pilot release acceptance. | All P0 acceptance criteria signed off. | P0 |

# 24. 90-Day Sprint Strategy

Assumption: 2-week sprints with a small cross-functional product/engineering team. Exact capacity must be calibrated to team size.

| Sprint | Focus | Primary Outcome |
| --- | --- | --- |
| Sprint 0 | Discovery lock, architecture, environments, backlog refinement. | Engineering-ready baseline. |
| Sprint 1 | Foundation, auth, roles, core data model, case states. | Secure operational skeleton. |
| Sprint 2 | Customer intake, Concierge inbox, lead qualification, case creation. | Request → Case works. |
| Sprint 3 | Scope builder, service catalogue, quote builder, approval. | Case → Quote works. |
| Sprint 4 | Payment integration, activation controls, customer case tracking. | Quote → Payment works. |
| Sprint 5 | Assignment, scheduling, representative profiles. | Payment → Assignment works. |
| Sprint 6 | Field mobile checklist, evidence capture, exceptions. | Assignment → Evidence works. |
| Sprint 7 | QC queue, rework, escalation, report workflow. | Evidence → QC works. |
| Sprint 8 | Customer report delivery, notifications, SLA alerts. | QC → Customer works. |
| Sprint 9 | Operations dashboard, commercial metrics, analytics, pilot hardening. | Management control + pilot readiness. |
| Sprint 10 | Pilot stabilization, security testing, UX fixes, performance and support runbook. | Production pilot release. |
| Sprint 11 | Real-customer learning cycle, fixes, instrumentation, automation candidates. | P0 evidence and next-release backlog. |

# 25. Sprint 0 — Engineering Readiness

Lock architecture boundaries.

Confirm canonical entities and identifiers.

Confirm case-state transition matrix.

Confirm permission matrix.

Confirm service definitions and quote calculation inputs.

Confirm payment provider.

Confirm messaging provider.

Confirm evidence storage approach.

Create environments and CI/CD.

Set up product analytics event schema.

Turn backlog into engineering tickets.

Define Definition of Ready and Definition of Done.

# 26. Definition of Ready

User story is unambiguous.

Acceptance criteria are testable.

Dependencies are identified.

Design/UX reference exists.

Data fields are defined.

Authorization requirements are defined.

External integration requirements are known.

Edge cases are documented where material.

Owner is assigned.

# 27. Definition of Done

Implemented.

Code reviewed.

Automated tests added for critical logic.

Acceptance criteria passed.

Authorization tested.

Audit event added where required.

Analytics event added where required.

Error/empty states handled.

Relevant documentation updated.

Deployed to test environment.

Product/Operations acceptance completed.

# 28. Dependency Map

| Capability | Depends On |
| --- | --- |
| Customer intake | Foundation + customer model |
| Case management | Foundation + data model |
| Quote | Case + service catalogue |
| Payment | Quote + case state |
| Assignment | Case + payment + provider |
| Field mobile | Assignment + scope + evidence |
| QC | Evidence + scope |
| Report | QC + evidence |
| Customer tracking | Case + notifications |
| Dashboard | Case + financial + analytics |
| AI Concierge | Customer intake + case schema + approved tools |
| Recurring monitoring | Completed case + service definitions + scheduling |

# 29. Critical Path

The P0 critical path is:

FOUNDATION → INTAKE → CASE → SCOPE/QUOTE → PAYMENT → ASSIGNMENT → FIELD → EVIDENCE → QC → REPORT

Any work that does not unblock this path should be challenged before consuming scarce P0 engineering capacity.

# 30. Parallel Workstreams

| Workstream | Can Run In Parallel |
| --- | --- |
| Security | Foundation + architecture. |
| UX | Customer, Concierge, Operations and Field screens. |
| Service data | Catalogue and pricing configuration. |
| AI | Prototype intake/summarization against stable schemas. |
| Analytics | Event definitions can be implemented alongside workflows. |
| Operations | Pilot SOPs and manual fallback can be prepared before full automation. |
| GTM | Customer acquisition can begin only with operational capacity and manual fallback. |

# 31. Manual Fallback Requirements

Because ASOJU is Concierge-first, every automated workflow needs an operational fallback during P0.

If AI fails, Concierge can continue manually.

If payment integration fails, Finance can reconcile through approved fallback procedure.

If field mobile fails, controlled evidence submission fallback exists.

If notification fails, Concierge can communicate manually.

If dashboard data is incomplete, Operations can use the case tracker.

If a workflow is not automated, the case must still remain auditable.

The product must fail gracefully into the operating team—not leave the customer stranded.

# 32. QA Test Matrix

| Area | Minimum Test Coverage |
| --- | --- |
| Authentication | Login, logout, session expiry, MFA for privileged users. |
| Authorization | Role access + case-level access + evidence access. |
| Case states | Valid transitions + invalid transitions. |
| Quote | Scope, exclusions, calculations, approval, revision. |
| Payment | Success, failure, duplicate callback, reconciliation. |
| Assignment | Eligibility, conflict, acceptance, reassignment. |
| Field | Checklist, evidence, exception, offline/sync behavior where supported. |
| QC | Pass, rework, escalate, fail. |
| Report | Approval, delivery, access. |
| Notifications | Critical events and duplicate prevention. |
| Audit | Actor, timestamp, object and state change. |
| AI | Grounding, escalation, high-risk boundary, prompt/tool abuse. |
| Analytics | Event firing and metric reconciliation. |

# 33. Pilot Release Checklist

| Item | Owner | Status |
| --- | --- | --- |
| Golden path passes end-to-end | Engineering/Product |  |
| Customer UX reviewed | Product/Customer Experience |  |
| Concierge workflow reviewed | Operations |  |
| Field workflow tested in realistic conditions | Operations/Field |  |
| QC workflow tested | Quality/Operations |  |
| Payment reconciliation tested | Finance |  |
| Security/access testing passed | Engineering/Security |  |
| Backup/restore tested | Engineering |  |
| Monitoring/alerts active | Engineering |  |
| Support runbook ready | Operations |  |
| Manual fallback ready | Operations |  |
| Pilot cohort selected | GTM |  |
| Success metrics configured | Product/Management |  |

# 34. Pilot Success Metrics

| Metric | Why It Matters |
| --- | --- |
| Lead → paid conversion | Commercial viability. |
| Quote → paid conversion | Value/pricing fit. |
| Assignment time | Operational responsiveness. |
| SLA adherence | Promise reliability. |
| QC first-pass rate | Quality. |
| Rework rate | Hidden delivery cost. |
| Report turnaround | Customer experience. |
| Customer satisfaction/trust | Core ASOJU promise. |
| Repeat rate | Retention. |
| Recurring conversion | Ongoing representation opportunity. |
| Referral rate | Trust-led growth. |
| Contribution/case | Economic viability. |

# 35. Product Decision Log

| Decision | Reason | Date | Owner | Status |
| --- | --- | --- | --- | --- |

# 36. P0 Backlog Governance

Product owns prioritization.

Operations owns operational correctness.

Customer Experience owns customer-facing language and flow.

Engineering owns technical implementation quality.

Finance validates commercial calculations.

Risk/security owns applicable controls.

Any change to locked case states requires explicit review.

Any high-risk AI capability requires explicit approval.

New scope must identify what P0 work it displaces if capacity is constrained.

# 37. Explicitly Deferred

Full marketplace discovery.

Uncontrolled nationwide provider marketplace.

Autonomous high-risk agent actions.

High-value third-party fund holding.

Large-scale service catalogue expansion.

Complex BI/data warehouse architecture.

Overbuilt mobile applications beyond the field workflow.

Broad consumer social/community features.

International expansion before Nigerian operating proof.

# 38. 90-Day Exit Criteria

The P0 build should be considered ready for broader pilot use only when:

The golden path works end-to-end.

Cases are auditable.

Customer and staff permissions are reliable.

Field representatives can execute and submit evidence.

QC controls are functioning.

Customers can receive and access reports.

Critical notifications work.

Payment and financial records reconcile.

Core dashboards provide trustworthy data.

Manual fallbacks are operationally ready.

No P0 no-go condition remains unresolved.

# 39. Final Engineering Principle

Do not build an impressive app that sits on top of an unproven operation.

Build the smallest reliable system that makes the ASOJU operating model repeatable, measurable and trustworthy.

The first release should make the team better at delivering trust—not merely give the team more screens.

# 40. Governance

Document owner: ASOJU Product / Technology / Operations.

Version: 1.0 | 90-Day P0 Build.

This backlog should be reviewed at every sprint boundary against real customer and operational evidence.