ASOJU 100-CUSTOMER GO-TO-MARKET PLAN

GTM v1.0 | First 100 Customers

Brand: ASOJU — Your Trusted Rep Back Home.

Purpose: turn the validated ASOJU proposition into a focused, measurable customer-acquisition system for the first 100 customers.

# 1. GTM Objective

The first 100 customers are not primarily a revenue target. They are ASOJU's market-validation engine.

Prove Nigerians abroad will pay for trusted representation.

Prove the strongest entry services and customer segments.

Prove customers trust ASOJU with increasingly important responsibilities.

Measure repeat purchase and recurring monitoring.

Generate referrals.

Establish delivery and acquisition economics.

# 2. First-100 Milestones

| Milestone | Customers | Purpose |
| --- | --- | --- |
| Validation cohort | 10 | Prove the basic proposition |
| Early traction | 25 | Test pricing and delivery |
| Product-market signal | 50 | Identify strongest services and segments |
| Commercial validation | 75 | Test referrals and recurring services |
| First 100 | 100 | Establish repeatable acquisition model |

The objective is not merely 100 one-off transactions; it is 100 customers with measurable trust, satisfaction, repeat/referral potential and service economics.

# 3. Geographic Strategy

| Market | Initial Focus | Priority | Working Customer Target |
| --- | --- | --- | --- |
| UK | London; then Birmingham, Manchester, Leicester, Bristol | Very High | 40 |
| USA | Houston; then Dallas, Atlanta, DC/MD/VA, New York/New Jersey | Very High | 35 |
| Canada | Toronto/GTA; then Calgary, Edmonton, Ottawa | High | 20 |
| Other | Selective opportunities | Test only | 5 |
| TOTAL |  |  | 100 |

These allocations are working hypotheses and should shift toward markets with the best qualified-lead conversion, service economics and referral potential.

# 4. Phase 1 Service Mix

| Service | Target Share | Role in GTM |
| --- | --- | --- |
| Property Verification | 25% | Acquisition / trust gateway |
| Construction Monitoring | 25% | High-value execution + recurring potential |
| Property/Asset Monitoring | 20% | Retention / recurring revenue |
| Concierge | 15% | Broad entry point and product-discovery engine |
| Business/Site Monitoring | 15% | Higher-value B2B expansion |

# 5. Acquisition Engine

Referral — highest strategic priority.

Diaspora communities — associations, professional groups, alumni and community networks.

Strategic partnerships — diaspora-facing professionals and organizations.

Educational content — problem-led, trust-building content.

Organic social — Facebook, Instagram, LinkedIn, YouTube and WhatsApp.

Paid acquisition — scale only after identifying a converting offer and message.

# 6. Referral Engine

After successful delivery, the customer should be invited to refer someone who needs a trusted rep back home.

Test service credits, priority benefits and other non-cash referral incentives.

Track referred lead source and conversion.

Reward successful referrals without undermining the premium positioning.

Use customer stories/testimonials only with explicit permission.

Target: 25 of the first 100 customers from referrals.

# 7. Diaspora Community Strategy

Nigerian associations

Professional groups

Alumni associations

Church communities

Cultural organizations

Business networks

Diaspora investment groups

Lead with useful education rather than hard selling. Example: “How to protect a construction project in Nigeria when you live abroad.”

# 8. Strategic Partnerships

| Partner | What they already provide | ASOJU role |
| --- | --- | --- |
| Real estate professionals | Property discovery/sales | Independent physical verification |
| Diaspora-focused lawyers | Legal advice/documentation | Physical verification/execution where appropriate |
| Accountants/financial professionals | Financial/tax guidance | Local operational execution |
| Immigration/travel professionals | Diaspora customer relationships | Nigeria-side support |
| Diaspora organizations | Community trust and reach | Preferred service/benefit partner |

Principle: do not compete with trusted professionals; become the execution partner they can refer.

# 9. Problem-Led Content

“5 things to verify before buying land in Nigeria from abroad.”

“Your contractor sent you photos. What should you check next?”

“Why sending someone ₦10m isn't the same as supervising ₦10m.”

“The hidden cost of managing Nigeria from abroad.”

“What would you check if you could physically be there?”

Content should sell the problem and the consequence before presenting the service.

# 10. Flagship Acquisition Offer

## ASOJU Property Verification

Core promise: “Know what is actually happening before you commit more money.”

Defined inspection scope

Verified field representative

Physical inspection

Structured checklist

Evidence

Findings

Quality control

Customer report

This is designed to become the trust gateway into the wider ASOJU relationship.

# 11. Concierge-First Funnel

The customer should not need to know which ASOJU service to buy.

| Stage | Customer experience | ASOJU action |
| --- | --- | --- |
| 1. Discover | Sees useful content or referral | Build trust |
| 2. State problem | “I need something handled back home.” | Concierge captures intent |
| 3. Qualify | Location, scope, urgency, evidence | AI + human qualification |
| 4. Quote | Clear scope, price and timeline | Operations prepares quote |
| 5. Authorize | Approves and pays | Case opened |
| 6. Execute | Work happens | Field network performs |
| 7. Verify | Evidence + QC | ASOJU validates |
| 8. Report | Customer receives outcome | Close case |
| 9. Continue | Needs ongoing oversight | Offer monitoring/representation |

# 12. Acquisition Funnel

CONTENT → PROBLEM → EDUCATION → TRUST → REQUEST VERIFICATION → FIRST SERVICE → REPEAT → RECURRING → REPRESENTATION

# 13. First-100 Acquisition Targets

| Channel | Target Customers |
| --- | --- |
| Referrals | 25 |
| Community partnerships | 20 |
| Strategic partners | 15 |
| Organic content | 15 |
| Direct outreach | 10 |
| Paid advertising | 10 |
| Events/networking | 5 |
| TOTAL | 100 |

# 14. 90-Day Execution Plan

## Days 1–30 — VALIDATE

Target: 10–20 customers.

Founder-led sales

Personal networks and diaspora communities

Referrals

Strategic partnerships

Avoid aggressive paid scaling before conversion evidence.

Primary question: Will people pay?

## Days 31–60 — REPEAT

Target: 30–40 cumulative customers.

Identify best service

Identify best customer segment

Identify best geography

Identify strongest acquisition channel

Test pricing and objections

Introduce recurring offer after successful cases.

Primary question: Can we repeat the acquisition pattern?

## Days 61–90 — SCALE

Target: 100 cumulative customers.

Increase referral activity

Expand partnerships

Scale winning content

Introduce controlled paid acquisition

Push recurring monitoring

Standardize high-performing workflows.

Primary question: Can acquisition and delivery become systematic?

# 15. Customer Data to Capture

| Area | Data Points |
| --- | --- |
| Acquisition | Source, country, city, referral, campaign, partner |
| Customer | Segment, age band, service, Nigeria location, asset/project value band |
| Commercial | Quote, amount paid, direct cost, contribution, CAC |
| Service | Completion time, evidence quality, QC outcome, rework, complaint |
| Relationship | Repeat purchase, recurring plan, referral, satisfaction/NPS |

# 16. North-Star Validation Metric

Do not optimize only for 100 transactions. Optimize for 100 Trust Events.

A Trust Event is a completed ASOJU assignment where the customer can credibly conclude: “They did what they said they would do.”

Trust Event → Repeat → Recurring → Referral → Representation

# 17. GTM Message Experiments

| Message | Primary Trigger | What to Measure |
| --- | --- | --- |
| Your Trusted Rep Back Home. | Trust / representation | CTR, qualified leads, payment conversion |
| From Distance to Done. | Execution / convenience | CTR, quote requests, conversion |
| Know What's Happening Before You Send More Money. | Risk reduction | Qualified leads, payment conversion |

Run the same core offer against different messages and compare qualified-lead and paid conversion, not vanity metrics alone.

# 18. First-100 Success Criteria

Who buys?

Why do they buy?

What do they buy first?

How much will they pay?

Where do they come from?

Why do they trust ASOJU?

What makes them return?

What makes them refer?

What does delivery actually cost?

Which services are profitable?

Which services should be stopped or redesigned?

# 19. GTM Operating Principles

Start narrow; expand from evidence.

Lead with trust and specific customer problems.

Use Concierge as the front door, not as an excuse for unlimited bespoke work.

Protect service quality during acquisition growth.

Do not compete primarily on lowest price.

Use first-party customer data to refine the ICP continuously.

Scale only the channels that produce qualified, profitable customers.

# 20. Strategic GTM Conclusion

The ASOJU acquisition journey is designed around one transformation:

WORRY → VERIFY → TRUST → MONITOR → REPRESENT

The commercial objective is to turn a first transaction into a trusted, recurring relationship.

ASOJU — Your Trusted Rep Back Home.

# 21. Immediate Execution Checklist

Finalize the Property Verification offer and deliverables.

Create the first landing page / request form.

Create WhatsApp Concierge qualification flow.

Prepare first quotation template.

Create first customer case/inspection workflow.

Recruit and train initial field representatives.

Build referral mechanism.

Identify first 20 diaspora community/partner opportunities.

Launch 3 message experiments.

Track every lead and case in the P0 execution tracker.

Review results weekly and reallocate acquisition effort toward the best-performing segment/channel.

Document status: GTM v1.0 — working execution plan. Targets are hypotheses for pilot management and should be updated from actual ASOJU data.