ASOJU P0 ENGINEERING BACKLOG & DEVELOPMENT ROADMAP

Epics • User Stories • Tasks • Dependencies • Acceptance Criteria • Launch Plan

Version 1.0 • Engineering Execution Plan
ASOJU — Your Trusted Rep Back Home.

# 1. Purpose

This document converts the approved ASOJU P0 Technical Build Specification into an executable engineering backlog. It is intended to let a product/engineering team plan, build, test and launch the P0 without losing the operating rules already established.

P0 scope remains Concierge, Verify and Projects. Arrival, Assets and Trade remain Phase 2.

# 2. P0 Definition of Done

Customer can submit a P0 service request.

Operations can intake, scope and quote the request.

Priority/Premium discounts and SC are calculated correctly.

Payment/authorization can release execution.

Operations can create and assign a Job Card.

Field Agent can execute and submit evidence.

QC can approve, reject, request revisit or escalate.

Customer receives an approved completion report.

Finance can reconcile payment, SC and external costs.

Material actions are audited.

Role-based access prevents unauthorized access.

# 3. Backlog Structure

| Level | Meaning |
| --- | --- |
| Epic | Major product/technical domain |
| Feature | Deliverable capability |
| User Story | User-centered behavior |
| Task | Engineering implementation unit |
| Acceptance Criteria | Testable completion condition |

# 4. Priority Model

| Priority | Meaning |
| --- | --- |
| P0-Critical | Required for pilot operation |
| P0-High | Required for complete/usable pilot |
| P0-Medium | Useful for pilot but can be simplified/manual |
| P1 | Post-P0 improvement |
| P2 | Phase 2/future |

# 5. Roadmap Overview

| Stage | Primary outcome |
| --- | --- |
| Sprint 0 | Foundation, environments, architecture and backlog setup |
| Sprint 1 | Authentication, users, roles and customer profile |
| Sprint 2 | Request intake + Case Engine |
| Sprint 3 | Scope + Quote Engine |
| Sprint 4 | Membership + SC + Payment |
| Sprint 5 | Operations + Scheduling + Job Cards |
| Sprint 6 | Field Agent + Evidence |
| Sprint 7 | QC + Reports + Notifications |
| Sprint 8 | Finance + Admin + Analytics |
| Sprint 9 | Security, QA, UAT and pilot hardening |
| Pilot | Controlled real-world launch |

# 6. EPIC A — Engineering Foundation

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| A-01 | Create source repository and branching strategy | P0-Critical | — |
| A-02 | Configure development/staging/production environments | P0-Critical | A-01 |
| A-03 | Set up CI/CD pipeline | P0-High | A-02 |
| A-04 | Create application/API shell | P0-Critical | A-01 |
| A-05 | Create database and migration framework | P0-Critical | A-04 |
| A-06 | Configure secrets/environment management | P0-Critical | A-02 |
| A-07 | Configure structured logging/error tracking | P0-High | A-04 |
| A-08 | Create design-system component foundation | P0-High | A-04 |

Acceptance: a clean deployment can reach staging with migrations, environment configuration and health checks working.

# 7. EPIC B — Authentication & Identity

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| B-01 | Customer registration/login | P0-Critical | A |
| B-02 | Phone/email verification | P0-Critical | B-01 |
| B-03 | Session management | P0-Critical | B-01 |
| B-04 | Password/OTP recovery flow | P0-High | B-01 |
| B-05 | Internal user creation | P0-Critical | B-01 |
| B-06 | Role assignment | P0-Critical | B-05 |
| B-07 | Account status controls | P0-High | B-05 |

Acceptance: users authenticate securely and cannot access resources outside their role/ownership.

# 8. EPIC C — Customer Profile

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| C-01 | Customer profile | P0-Critical | B |
| C-02 | Country/time zone | P0-High | C-01 |
| C-03 | Communication preferences | P0-High | C-01 |
| C-04 | Saved addresses | P0-High | C-01 |
| C-05 | Customer case history | P0-Critical | Case Engine |

Acceptance: customer can manage relevant profile information and view only their own cases.

# 9. EPIC D — Case Engine

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| D-01 | Create Case entity | P0-Critical | A,C |
| D-02 | Case ID generation | P0-Critical | D-01 |
| D-03 | Case state machine | P0-Critical | D-01 |
| D-04 | Case owner assignment | P0-Critical | B |
| D-05 | Case timeline/events | P0-Critical | D-03 |
| D-06 | Case search/filter | P0-High | D-01 |
| D-07 | Customer case view | P0-Critical | D |
| D-08 | Operations case workspace | P0-Critical | D |
| D-09 | Action Needed state | P0-High | D-03 |
| D-10 | Exception state | P0-High | D-03 |
| D-11 | Case cancellation | P0-High | D-03 |

Acceptance: the full normal and exception state machine is enforced server-side and reflected in customer/internal UI.

# 10. EPIC E — Service Intake

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| E-01 | Service-family selection | P0-Critical | D |
| E-02 | Concierge intake questions | P0-Critical | E-01 |
| E-03 | Verify intake questions | P0-Critical | E-01 |
| E-04 | Projects intake questions | P0-Critical | E-01 |
| E-05 | Attachment intake | P0-High | E-01 |
| E-06 | Request review/submit | P0-Critical | E-02–E-05 |
| E-07 | Operations clarification workflow | P0-Critical | E-06 |

Acceptance: each P0 service can collect enough structured information to create a quote without forcing one universal form.

# 11. EPIC F — Scope & Job Definition

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| F-01 | Scope builder | P0-Critical | D,E |
| F-02 | Task list | P0-Critical | F-01 |
| F-03 | Deliverables | P0-Critical | F-01 |
| F-04 | Exclusions | P0-Critical | F-01 |
| F-05 | Evidence requirements | P0-Critical | F-01 |
| F-06 | Scope versioning | P0-Critical | F-01 |
| F-07 | Customer scope confirmation | P0-Critical | F-06 |

Acceptance: material scope changes create a traceable new version and cannot silently expand execution.

# 12. EPIC G — Quote Engine

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| G-01 | Quote entity | P0-Critical | F |
| G-02 | Quote line categories | P0-Critical | G-01 |
| G-03 | ASOJU Service Fee calculation | P0-Critical | G-02 |
| G-04 | External-cost lines | P0-Critical | G-02 |
| G-05 | Third-party professional fee lines | P0-Critical | G-02 |
| G-06 | Quote versioning | P0-Critical | G-01 |
| G-07 | Quote validity/expiry | P0-High | G-06 |
| G-08 | Customer quote view | P0-Critical | G |
| G-09 | Accept/request-change/decline | P0-Critical | G-08 |
| G-10 | FX display + NGN execution fields | P0-Critical | G-03 |

Acceptance: a customer can clearly distinguish ASOJU fees, membership benefits and external/third-party costs, and accepted quote amounts remain traceable.

# 13. EPIC H — Membership & SC

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| H-01 | Priority plan configuration | P0-Critical | A |
| H-02 | Premium plan configuration | P0-Critical | A |
| H-03 | Membership lifecycle | P0-Critical | H-01,H-02 |
| H-04 | SC ledger | P0-Critical | H-03 |
| H-05 | SC grant | P0-Critical | H-04 |
| H-06 | SC debit | P0-Critical | H-04,G |
| H-07 | SC reversal/adjustment | P0-High | H-04 |
| H-08 | 10% Priority discount | P0-Critical | H-01,G |
| H-09 | 15% Premium discount | P0-Critical | H-02,G |
| H-10 | Eligible request allowance tracking | P0-Critical | H-03,D |
| H-11 | Customer membership UI | P0-High | H |

Acceptance: Priority is $99/month with $50 SC and 10% discount; Premium is $299/month with $150 SC and 15% discount; eligible usage is traceable.

# 14. EPIC I — Payment & Financial Authorization

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| I-01 | Payment adapter interface | P0-Critical | G |
| I-02 | Payment initiation | P0-Critical | I-01 |
| I-03 | Payment webhook handling | P0-Critical | I-02 |
| I-04 | Webhook idempotency | P0-Critical | I-03 |
| I-05 | Payment state machine | P0-Critical | I-03 |
| I-06 | Execution release gate | P0-Critical | I-05,H |
| I-07 | Payment failure UI | P0-High | I-05 |
| I-08 | Refund/reversal support | P0-Medium | I-05 |

Acceptance: execution cannot be released without the required payment or valid SC authorization and any required external-cost authorization.

# 15. EPIC J — Operations Dashboard

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| J-01 | Operations dashboard | P0-Critical | D |
| J-02 | Request queue | P0-Critical | E |
| J-03 | Case filters | P0-High | D |
| J-04 | Quote queue | P0-High | G |
| J-05 | Payment blockers | P0-High | I |
| J-06 | Active jobs view | P0-Critical | K |
| J-07 | Exception queue | P0-High | D |
| J-08 | QC queue | P0-Critical | M |

# 16. EPIC K — Scheduling & Job Cards

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| K-01 | Field Agent profile | P0-Critical | B |
| K-02 | Agent availability/capacity | P0-High | K-01 |
| K-03 | Schedule view | P0-Critical | K-01,D |
| K-04 | Job Card generation | P0-Critical | F,I |
| K-05 | Job assignment | P0-Critical | K-01,K-04 |
| K-06 | Double-booking warning | P0-Medium | K-03 |
| K-07 | Job Card revision on approved scope change | P0-Critical | F,K-04 |

Acceptance: Field Agents receive only authorized Job Cards and only approved scope appears on the execution record.

# 17. EPIC L — Field Agent Workspace

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| L-01 | Agent Today screen | P0-Critical | K |
| L-02 | Job Detail | P0-Critical | K |
| L-03 | Start Job | P0-Critical | K |
| L-04 | Task checklist | P0-Critical | K |
| L-05 | Evidence capture | P0-Critical | N |
| L-06 | Exception escalation | P0-Critical | D |
| L-07 | Completion submission | P0-Critical | L-04,L-05 |
| L-08 | Agent history | P0-Medium | L |

# 18. EPIC M — Evidence & QC

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| M-01 | Private object storage | P0-Critical | A |
| M-02 | Evidence metadata | P0-Critical | D,L |
| M-03 | Secure upload | P0-Critical | M-01,M-02 |
| M-04 | Task/evidence linkage | P0-Critical | M-02 |
| M-05 | Evidence access control | P0-Critical | B,M-02 |
| M-06 | QC queue | P0-Critical | L |
| M-07 | QC checklist | P0-Critical | F |
| M-08 | Pass | P0-Critical | M-06,M-07 |
| M-09 | Pass with limitation | P0-Critical | M-06 |
| M-10 | Fail/correction | P0-Critical | M-06 |
| M-11 | Revisit required | P0-Critical | M-06,K |
| M-12 | Escalation | P0-Critical | M-06 |

Acceptance: evidence remains private, linked to case/task, and QC outcomes control the closure path.

# 19. EPIC N — Customer Reports

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| N-01 | Report template by service | P0-Critical | M,F |
| N-02 | Report generation | P0-Critical | N-01 |
| N-03 | Evidence embedding/links | P0-Critical | M |
| N-04 | External-cost section | P0-Critical | O |
| N-05 | QC approval | P0-Critical | M |
| N-06 | Customer delivery | P0-Critical | N-05 |

Acceptance: a report cannot be delivered as completed unless the required QC gate is satisfied.

# 20. EPIC O — Finance & Reconciliation

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| O-01 | Finance dashboard | P0-High | I |
| O-02 | Payment records | P0-Critical | I |
| O-03 | SC ledger view | P0-Critical | H |
| O-04 | External cost records | P0-Critical | G |
| O-05 | Authorized vs actual | P0-Critical | O-04 |
| O-06 | Reconciliation queue | P0-Critical | O-02,O-05 |
| O-07 | Manual adjustment workflow | P0-High | O-06 |

# 21. EPIC P — Notifications & WhatsApp

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| P-01 | Notification event framework | P0-Critical | D |
| P-02 | In-app notifications | P0-Critical | P-01 |
| P-03 | Email adapter | P0-High | P-01 |
| P-04 | WhatsApp adapter | P0-High | P-01 |
| P-05 | Quote notification | P0-Critical | G,P |
| P-06 | Payment notification | P0-Critical | I,P |
| P-07 | Status notification | P0-High | D,P |
| P-08 | Action-needed notification | P0-Critical | D,P |
| P-09 | Completion notification | P0-Critical | N,P |

# 22. EPIC Q — Admin & Configuration

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| Q-01 | Admin users/roles | P0-Critical | B |
| Q-02 | Service configuration | P0-High | E |
| Q-03 | Pricing configuration | P0-Critical | G |
| Q-04 | Membership configuration | P0-Critical | H |
| Q-05 | SC eligibility configuration | P0-Critical | H |
| Q-06 | QC checklist configuration | P0-High | M |
| Q-07 | Notification templates | P0-High | P |
| Q-08 | Audit log viewer | P0-Critical | R |

# 23. EPIC R — Audit & Security

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| R-01 | Audit event model | P0-Critical | A |
| R-02 | Material action logging | P0-Critical | D–Q |
| R-03 | RBAC tests | P0-Critical | B |
| R-04 | Case ownership authorization tests | P0-Critical | D |
| R-05 | Evidence access tests | P0-Critical | M |
| R-06 | Webhook signature verification | P0-Critical | I |
| R-07 | Rate limiting | P0-High | B |
| R-08 | Secure file validation | P0-Critical | M |
| R-09 | Sensitive logging review | P0-High | A |

# 24. EPIC S — Analytics

| ID | Story/Task | Priority | Depends on |
| --- | --- | --- | --- |
| S-01 | Core event taxonomy | P0-High | D |
| S-02 | Request metrics | P0-High | S-01 |
| S-03 | Quote acceptance | P0-High | G |
| S-04 | Payment conversion | P0-High | I |
| S-05 | SC usage | P0-High | H |
| S-06 | Execution metrics | P0-High | K,L |
| S-07 | QC metrics | P0-High | M |
| S-08 | Customer satisfaction | P0-High | N |
| S-09 | Membership retention | P0-High | H |

# 25. EPIC T — QA, UAT & Pilot Hardening

| ID | Task | Priority | Depends on |
| --- | --- | --- | --- |
| T-01 | Automated unit test suite | P0-Critical | All core modules |
| T-02 | Integration test suite | P0-Critical | Core modules |
| T-03 | End-to-end golden-path tests | P0-Critical | Customer→Closure |
| T-04 | Failure-path tests | P0-Critical | D–P |
| T-05 | Security/access tests | P0-Critical | R |
| T-06 | Payment/SC calculation tests | P0-Critical | H,I |
| T-07 | Mobile field usability test | P0-High | L |
| T-08 | Operations UAT | P0-Critical | J–Q |
| T-09 | Customer UAT | P0-Critical | B–N |
| T-10 | Pilot incident/runbook | P0-High | All |
| T-11 | Production readiness review | P0-Critical | T-01–T-10 |

# 26. Golden-Path Development Scenario

The first complete vertical slice should be a real Concierge case:

Customer request → Case → Intake → Scope → Quote → Priority/Premium calculation where applicable → Payment/SC authorization → Job Card → Field Agent execution → Evidence → QC → Completion Report → Customer notification → Closure.

This should be demonstrated end-to-end before building large amounts of secondary functionality.

# 27. Critical Business Rules to Encode

All normal services are quoted and paid/authorized before execution.

Member discounts apply to eligible ASOJU Service Fees.

Priority discount = 10%.

Premium discount = 15%.

Priority = $99/month + $50 SC + up to 2 eligible Concierge requests/month.

Premium = $299/month + $150 SC + up to 5 eligible Concierge requests/month.

SC is ledger-based and not cash.

External/third-party costs are quoted separately.

ASOJU field transport/logistics can be part of the ASOJU fee when included in the quote.

Accepted quotes cannot be silently altered.

Field Agents execute approved Job Cards.

QC controls normal completion.

# 28. Sprint 0 — Foundation

Repository and branching.

Environment setup.

Database schema baseline.

API shell.

Authentication architecture.

Design-system foundation.

CI/CD.

Logging/error tracking.

Backlog imported into issue tracker.

Exit: engineering team can deploy a minimal authenticated shell to staging.

# 29. Sprint 1 — Identity

Customer auth/profile.

Internal users.

RBAC.

Basic navigation shells.

Audit foundation.

Exit: each role can authenticate and sees only authorized surfaces.

# 30. Sprint 2 — Request + Case

Service selection.

Intake forms.

Case creation.

State machine.

Case timeline.

Customer case view.

Operations request queue.

Exit: customer can create a case and Operations can manage it through intake.

# 31. Sprint 3 — Scope + Quote

Scope builder.

Scope versioning.

Quote builder.

Quote line categories.

FX/NGN fields.

Quote customer view.

Quote acceptance/change/decline.

Exit: a complete quote can be generated, accepted and audited.

# 32. Sprint 4 — Membership + Payments

Priority/Premium plans.

Membership state.

SC ledger.

Discount rules.

Payment adapter.

Payment webhooks.

Execution release gate.

Exit: commercial lifecycle is testable end-to-end.

# 33. Sprint 5 — Operations + Field

Operations dashboard.

Agent profiles.

Scheduling.

Job Card generation.

Assignment.

Field Today.

Job Detail.

Start/Checklist/Completion.

Exit: an authorized case can be dispatched to a Field Agent.

# 34. Sprint 6 — Evidence + QC

Secure storage.

Evidence capture.

Metadata.

Access controls.

QC queue.

QC decisions.

Revisit/escalation.

Exit: field submission can pass through QC with controlled outcomes.

# 35. Sprint 7 — Reports + Notifications

Report templates.

Report generation.

Customer delivery.

In-app notifications.

Email/WhatsApp integration boundary.

Action-needed messaging.

Exit: customer receives a complete, QC-approved outcome.

# 36. Sprint 8 — Finance + Admin + Analytics

Finance dashboard.

Reconciliation.

External-cost management.

Admin configuration.

Audit viewer.

Core analytics.

Exit: management can operate and measure the pilot.

# 37. Sprint 9 — Hardening

Security testing.

Regression testing.

Mobile usability.

Performance checks.

Backup/restore test.

UAT.

Pilot runbook.

Production readiness review.

Exit: P0 launch gate passed.

# 38. Pilot Launch Gate

| Area | Pass condition |
| --- | --- |
| Product | Golden path works |
| Operations | Team can run cases without developer intervention for normal cases |
| Commercial | Quotes/payment/SC reconcile |
| Field | Agents can execute and submit evidence |
| QC | Reports are consistently reviewable |
| Security | No critical unresolved access/security issue |
| Customer | UAT participants understand status/actions |
| Support | Escalation/runbook exists |
| Analytics | Core pilot metrics visible |

# 39. Post-Launch Week 1

Daily operational review.

Review every exception.

Review every QC failure.

Check payment/SC reconciliation.

Collect customer feedback.

Fix P0 defects before adding features.

Track field-agent bottlenecks.

# 40. Post-Launch Week 2–4

Analyze repeat usage.

Analyze membership behavior.

Identify manual bottlenecks.

Prioritize automation only where measured.

Refine service templates.

Refine pricing based on evidence, not guesswork.

Prepare Phase 2 only after P0 stability.

# 41. Engineering Metrics

| Metric | Purpose |
| --- | --- |
| Lead time | Delivery speed |
| Deployment frequency | Release capability |
| Change failure rate | Release quality |
| Mean time to recovery | Operational resilience |
| Defect escape rate | QA quality |
| P0 acceptance pass rate | Feature quality |
| API error rate | Technical health |
| Payment reconciliation failures | Financial health |
| Evidence upload failure rate | Field reliability |

# 42. Product/Operations Metrics

| Metric | Purpose |
| --- | --- |
| Request volume | Demand |
| Quote acceptance | Commercial fit |
| Average ASOJU fee | Unit economics |
| SC utilization | Membership economics |
| On-time execution | Reliability |
| QC first-pass | Quality |
| Revisit rate | Field quality |
| Customer satisfaction | CX |
| Repeat rate | Retention |
| Membership renewal | Subscription health |

# 43. Backlog Governance

Product owns priority.

Engineering owns technical sequencing within approved priority.

Operations validates workflow behavior.

Finance validates commercial logic.

QC validates evidence/report behavior.

Security/privacy validates sensitive controls.

No scope addition to P0 without explicit impact assessment.

# 44. Change Control

| Change | Action |
| --- | --- |
| Bug affecting core workflow | P0 fix |
| Security issue | Immediate priority |
| Commercial rule change | Product + Finance approval |
| New service family | P1/Phase 2 unless P0 explicitly re-approved |
| New integration | Assess dependency/security/maintenance impact |
| UX refinement | Can enter normal design/engineering queue |

# 45. Phase 2 Backlog Placeholder

| Domain | P2 direction |
| --- | --- |
| Arrival | Pre-arrival planning, airport pickup, settlement-in-Nigeria support |
| Assets | Asset inspection, management and ongoing oversight |
| Trade | Import/export support and trade coordination |
| Advanced automation | AI-assisted intake, quoting, routing and reporting |
| Provider network | Structured provider marketplace/network |
| Multi-country | Additional operating countries |

# 46. What the Engineering Team Should Build First

Do not start by building every screen. Build the first complete vertical slice:

**Customer request → Case → Scope → Quote → Payment/SC → Job Card → Field Agent → Evidence → QC → Report → Closure.**

Then harden that slice before expanding horizontally.

# 47. Final P0 Backlog Rule

Every backlog item must answer four questions:

What user/business problem does this solve?

What existing ASOJU rule does it implement?

What dependency does it have?

How will we know it is done?

If a proposed feature cannot answer these questions, it should not enter the P0 engineering backlog without further definition.

# 48. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Founder/General Manager |  |  |  |
| Product Lead |  |  |  |
| Technical Lead |  |  |  |
| Operations Lead |  |  |  |
| Finance |  |  |  |
| QC Lead |  |  |  |
| Security/Privacy |  |  |  |